## RAID Dashboard
RAID Dashboard
Total RAIDs |  | Risks | Assumptions |  | Issues |  | Dependencies |  | RAID Dashboard
[9 empty] | Select RAID Type | Assumption
17 |  | 6 | 4 |  | 3 |  | 4
| Status | Count | Category | Count |  | Mitigation | Count
| Not Started | 0 | Cost | 0 |  | Avoid | 0
| In-Progress | 2 | Process | 1 |  | Mitigate | 0
| Behind | 2 | Quality | 0 |  | Transfer | 0
| Closed | 0 | Resource | 0 |  | Escalate | 0
|  |  | Scope | 0 |  | Accept | 4 |  |  |  | Category Label Compact | Count Compact
|  |  | Security/Compliance | 1
|  |  | Stakeholder | 1
|  |  | Technical | 1
| Status Label | Count | Mitigation Label | Count |  |  | Category Label | Count
#N/A
| In-Progress | 2 |  | #N/A |  |  | Process | 1
| Behind | 2 |  | #N/A
#N/A
|  |  | Accept | 4
[7 empty] | Security/Compliance | 1
[7 empty] | Stakeholder | 1
[7 empty] | Technical | 1

## Project Cover Sheet
Project Name
Integrated Project Management Workbook |  |  |  |  | #REF!
Project Overview |  |  | Schedule & Commercials
Project Name | PMO Dashboard |  | Start Date | 2026-03-12
Client | Zapcom - Internal |  | Forecast End | 2026-05-30
Project Manager | Daksh Hooda |  | Duration (Days) | 79
Project Sponsor | Santhosh Nebalan |  | Budget | 10000
Complexity | Medium |  | Benefits
Execution Snapshot |  | RAID Snapshot |  | Team & Governance
15 | 10 | 6 | 3 | 4 |  | 10
Total Tasks | Completed | Open Risks | Open Issues | Stakeholders |  | Resources
4 | 3 | 4 | 0 | 0
In Progress | Tracked Milestones | Open Dependencies | Change Requests | Cadences |  | Report Date
Quick Navigation & Notes
Use this sheet as the front page of the workbook. It pulls summary fields from Project Charter and high-level counts from the core tracking tabs. |  |  |  | Go to Project Charter |  | Go to Project Plan
Best practice: update Project Charter first, then maintain Project Plan / RAID / Stakeholder / Resource sheets. The cover sheet will reflect the latest picture.
|  |  |  | Go to RAID Dashboard |  | Go to Risk Register
Single source of truth for charter, schedule, RAID, stakeholders, resources, changes, and milestone tracking.
|  |  |  | Go to Stakeholders |  | Go to Milestones

## Project Charter
PMO Dashboard
Project Name: | PMO Dashboard |  | Project Manager: | Daksh Hooda |  |  | Project Sponsor: | Santhosh Nebalan
Project Start Date: | 2026-03-12 |  | Estimated Duration: | 79 |  |  | Forecast End Date: | 2026-05-30
Estimated Budget: | 10000 |  | Estimated Benefits: | 0 |  |  | Project Complexity: | Medium
Business Case: |  |  |  |  | Project Deliverables:
Gap identification between 17.2 & 24.1 for Airlines. Gap identification, documentation, and conversion to user stories/change requests. |  |  |  |  | Gap document Detailed user stories Modified 24.1 test scripts Repository of anonymized 17.2 Request/Response pairs
Scope: |  |  |  |  | Milestones:
Included |  | Excluded |  |  | ID | Milestone Title |  |  | Estimated Start | Estimated Finish
Migrate 6 airlines from NDC 17.2 to NDC 24.1 by 2027 |  | Any code changes, enhancements, or defect fixes identified during testing in Phase 1 will be handled in Phase2 |  |  |  | Project Kickoff |  |  | 2026-03-12 | 2026-03-12
Approach in two phases, Gap analysis and migration to work in parallel |  | Changes to test case framework generator (TCG) not covered in this scope |  |  |  | Infrastructure & Deployment Environment Setup |  |  | 2026-03-13 | 2026-03-17
In Scope Airlines: AA, UA, WY, AM |  | Validation of new NDC 24.1 features not part of existing airline customizations is out of scope. |  |  |  | Project View Completed |  |  | 2026-03-18 | 2026-04-10
Production data mirroring and execution of shopping transactions for top agencies using traffic patterns |  | Airlines out of scope: LHG, COPA, ET, OA, A3, DL, KE, TS, 4Z, QF, HA, AS, EK, WS |  |  |  | Portfolio View |  |  | 2026-04-13 | 2026-04-30
|  | SPRK, Agency certification |  |  |  | Staff Augmentation View
|  | UAT and production deployment |  |  |  | Performance View
Top 3 Risks:
ID | Risk/Issue Description | Risk Rating | Mitigation/Action Plan
HIGH
MEDIUM
LOW
Project Approval:

## Project Plan
Task ID | WBS | Phase | Task Name | Task Type | Predecessor ID | Owner | Support Team / Function | Planned Start Date | Planned End Date | Duration (Days) | Actual Start Date | Actual End Date | Status | % Complete | Add to Milestone Tracker | Baseline Start Date | Baseline End Date | Variance (Days) | RAG Status | Comments / Notes | _MilestoneSeq
T-001 | 1 | Initiation | Project Kickoff | Milestone |  | Project Manager | PMO | 2026-04-01 | 2026-04-01 | 1 | 2026-04-02 | 2026-04-03 | Completed | 100% | ☑ | 2026-04-01 | 2026-04-01 | 2 | Green | Formal kickoff with sponsor and core team | 1
T-002 | 1.1 | Planning | Requirements Finalization | Task | T-001 | Project Manager | PMO | 2026-03-19 | 2026-03-18 | 0 | 2026-04-02 | 2026-04-03 | NA | 100% | ☐ | 2026-04-02 | 2026-04-08 | -5 | Red | Confirm technical structure and local build approach
T-003 | 1.2 | Planning | Solution Design Sign-off | Task | T-002 | Developer | Business Intelligence | 2026-04-10 | 2026-04-10 | 1 |  |  | Completed | 100% | ☐ | 2026-04-10 | 2026-04-10 | 0 | Green | Confirm technical structure and local build approach
T-004 | 2 |  | Project View Requirements & Layout Finalization | Task | T-003 | Developer | Business Intelligence | 2026-04-11 | 2026-04-24 | 14 |  |  | Completed | 100% | ☐ | 2026-04-11 | 2026-04-24 | 0 | Green | Finalize project detail page scope, tabs, actions, and metrics
T-005 | 2.1 |  | Infrastructure & Deployment Environment Setup | Milestone | T-004 | Developer | Business Intelligence | 2026-05-01 | 2026-05-01 | 1 |  |  | Completed | 100% | ☑ | 2026-05-01 | 2026-05-01 | 0 | Green | EC2, Node.js, MongoDB, PM2, Nginx, security group configuration | 2
T-006 | 2.2 |  | Application Deployment & Hosting Configuration | Task | T-005 | Developer | Business Intelligence | [5 empty] | Completed | 100% | ☐ |  |  |  | Green | Clone repo, install dependencies, build React app, configure reverse proxy
T-007 | 2.3 |  | Project Detail Page Development | Task | T-006 | Developer + UI/UX | [6 empty] | Completed | 100% | ☐ |  |  |  | Green | Build project header, action buttons, navigation, permissions, and layout
T-008 | 2.4 |  | Project Tabs & Document Categories Setup | Task | T-007 | Developer | Business Intelligence | [5 empty] | Completed | 100% | ☐ |  |  |  | Green | Configure tabs for charter, plan, milestones, stakeholders, governance, RAID, risk, resource, change, closure
T-009 | 2.5 |  | Excel Data Integration & Parsing Setup | Task | T-008 | Developer | Business Intelligence | [5 empty] | Completed | 100% | ☐ |  |  |  | Green | Parse workbook sheets, convert Excel dates, filter empty rows
T-010 | 2.6 |  | Backend APIs for Project View | Task | T-009 | Developer | Business Intelligence | [5 empty] | Completed | 100% | ☐ |  |  |  | Green | Project details, document retrieval, project update, document upload APIs
T-011 | 2.7 |  | Dashboard Metrics & Logic Implementation | Task | T-010 | UI/UX | [6 empty] | Completed | 100% | ☐ |  |  |  | Green | Planned vs actual, milestone completion, upcoming milestones, overdue items, risks, issues, aged RAID
T-012 | 2.8 |  | Bug Fixes & Functional Corrections | Task | T-011 | Developer | Business Intelligence | [5 empty] | In Progress |  | ☐ |  |  |  | Green | Portfolio endpoint, governance date conversion, meeting name mapping, governance compliance card
T-013 | 2.9 |  | UI Review & Dashboard Refinement | Task | T-012 | UI/UX | [6 empty] | In Progress |  | ☐ |  |  |  | Green | Improve layout, navigation, placeholders, icons, and overall presentation
T-014 | 2.1 |  | Documentation & Deployment Notes | Task | T-013 | Project Manager | PMO | [5 empty] | In Progress |  | ☐ |  |  |  | Green | Document deployment workflow, Excel handling points, and future update process
T-015 | 2.11 |  | Project View Completed | Milestone | T-014 | Project Manager | PMO | [5 empty] | In Progress |  | ☑ |  |  |  | Green | Phase 1 milestone – Project View completed and validated | 3
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
T-001
Formulas:
RAG Status = IF([Task ID]="","",IF([Status]="Completed","Green",IF(AND([Planned End Date]<>"",TODAY()>[Planned End Date]),"Red",IF(AND([Planned End Date]<>"",TODAY()+3>=[Planned End Date]),"Amber","Green"))))

## Milestone Tracker
Milestone Ref | WBS | Phase | Milestone / Task Name | Owner | Planned Start Date | Planned End Date | Actual End Date | Status | % Complete | Baseline End Date | Variance (Days) | RAG Status | Notes | _MilestoneSeq
T-001 | 1 | Initiation | Project Kickoff | Project Manager | 2026-04-01 | 2026-04-01 | 2026-04-03 | Completed | 100% | 2026-04-01 | 2 | Green | Formal kickoff with sponsor and core team | 1
T-005 | 2.1 | 0 | Infrastructure & Deployment Environment Setup | Developer | 2026-05-01 | 2026-05-01 | 0 | Completed | 100% | 2026-05-01 | 0 | Green | EC2, Node.js, MongoDB, PM2, Nginx, security group configuration | 2
T-015 | 2.11 | 0 | Project View Completed | Project Manager | 0 | 0 | 0 | In Progress | 0% | 0 |  | Green | Phase 1 milestone – Project View completed and validated | 3

## Risk Register
ID | Helper_Row | Risk Description | Risk Effect on Objectives | Impact Area | Impact Category | Impact Rating | Probability | Risk Score | Risk Priority | Risk Ranking | Status | Risk Owner | Date Raised | Closed Date | Mitigation Strategy | Risk Response
1 | 2 | Requirements for different dashboard views may change during development and affect timelines. | Close remaining mappings and confirm acceptance criteria. | Schedule | Schedule | Major | High | 16 | High | 1 | In-Progress | Daksh Hooda | 2026-02-20 |  | Mitigate
3 | 4 | Development may slow if metrics, layouts, and feature expectations are not finalized on time. | Increase cadence and improve closure-focused working sessions. | Schedule | Schedule | Major | High | 16 | High | 2 | Behind | Daksh Hooda | 2026-02-24 |  | Mitigate
4 | 5 | Stakeholders may expect a different final output if requirements are not clearly documented. | Confirm readiness inputs. | Scope | Scope | Major | Average | 12 | Moderate | 3 | In-Progress | Daksh Hooda | 2026-02-27 |  | Mitigate
5 | 6 | Portfolio/project metrics may show incorrect results if logic is not standardized. | Complete retesting and validate corrected mapping before closure. | Quality | Quality | Major | Average | 12 | Moderate | 4 | In-Progress | Daksh Hooda / Lalith Gali | 2026-03-09 |  | Mitigate
6 | 7 |  | Secure owners and ETA for the remaining mappings. | Schedule | Schedule | Major | Average | 12 | Moderate | 5 | In-Progress | Daksh Hooda | 2026-03-18 |  | Mitigate
7 | 8 | AWS approval delays may affect next-step transition planning. |  | Security/Compliance | Security/Compliance | Moderate | Average | 9 | Moderate | 6 | In-Progress | Santhosh Nebalan | 2026-03-18 |  | Accept
Formulas:
Date Raised = IF([Helper_Row]="","",IF(IFERROR(INDEX('RAID Log'!$1:$1048576,[Helper_Row],MATCH("Date Raised",'RAID Log'!$1:$1,0)),"")="","",IFERROR(INDEX('RAID Log'!$1:$1048576,[Helper_Row],MATCH("Date Raised",'RAID Log'!$1:$1,0)),"")))

## RAID Log
RAID ID | Type | Category | Impact Area | Title | Description | Impact/Effect of the RAID | Date Raised | RAID Owner | Impact Rating | Initial Probability | Severity | Target Date | Status | Mitigation Strategy | Next Update | Closed Date | RAID Response/Plan | Risk Seq
1 | Risk | Scope | Schedule | Requirements may continue to evolve across phases | Requirements for different dashboard views may change during development and affect timelines. | Close remaining mappings and confirm acceptance criteria. | 2026-02-20 | Daksh Hooda | Major | High | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25 |  |  | 1
3 | Risk | Process | Schedule | Delays in requirement clarification may impact development | Development may slow if metrics, layouts, and feature expectations are not finalized on time. | Increase cadence and improve closure-focused working sessions. | 2026-02-24 | Daksh Hooda | Major | High | High | 2026-03-25 | Behind | Mitigate | 2026-03-25 |  |  | 2
4 | Risk | Stakeholder | Scope | Misalignment between business expectation and delivered view | Stakeholders may expect a different final output if requirements are not clearly documented. | Confirm readiness inputs. | 2026-02-27 | Daksh Hooda | Major | Average | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25 |  |  | 3
5 | Risk | Quality | Quality | Metric definitions may be interpreted inconsistently | Portfolio/project metrics may show incorrect results if logic is not standardized. | Complete retesting and validate corrected mapping before closure. | 2026-03-09 | Daksh Hooda / Lalith Gali | Major | Average | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25 |  |  | 4
6 | Risk | Resource | Schedule | Small project team may create execution bottlenecks | Delivery may be impacted if one team member is unavailable or overloaded. | Secure owners and ETA for the remaining mappings. | 2026-03-18 | Daksh Hooda | Major | Average | Medium | 2026-03-25 | In-Progress | Mitigate | 2026-03-25 |  |  | 5
7 | Risk | Security/Compliance | Security/Compliance | Access for future deployment may not be available on time | AWS approval delays may affect next-step transition planning. |  | 2026-03-18 | Santhosh Nebalan | Moderate | Average | Medium | 2026-03-31 | In-Progress | Accept | 2026-03-25 |  |  | 6
8 | Assumption | Stakeholder | Schedule | Leadership will review and approve the POC after phase completion | Assumes leadership feedback and approval will be available after major milestones. |  | 2026-03-18 | Daksh Hooda | Major | Average | Medium | 2026-03-25 | In-Progress | Accept | 2026-03-25
9 | Assumption | Process | Other | Phase requirements will remain stable once finalized | Assumes minimal rework after requirement freeze. | Call out retest-driven moves in the weekly narrative to avoid confusion. | 2026-03-18 | Daksh Hooda | Moderate | Average | Medium | 2026-03-25 | In-Progress | Accept | 2026-03-25
10 | Assumption | Technical | Other | Existing tech stack is sufficient | Assumes no major technical redesign is required during the current stage. |  | 2026-03-17 | Lalith Gali | Moderate | Low | Low | 2026-03-31 | Behind | Accept | 2026-03-25
11 | Assumption | Security/Compliance | Security/Compliance | Future cloud hosting will use approved AWS services | Assumes EC2, S3, and CDK will be the eventual approved path. | Work priority list with ETAs; convert clarifications into worked closures. | 2026-03-17 | Santhosh Nebalan | Moderate | Average | Medium | 2026-03-25 | Behind | Accept | 2026-03-25
12 | Issue | Process | Schedule | Project plan and backlog were initially not aligned | Planning documents required restructuring to match phase/milestone/task logic. | Move to 2x weekly working sessions and track worked conversion. | 2026-03-17 | Daksh Hooda | Major | High | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25
13 | Issue | Scope | Quality | Backlog items need restructuring by phase and task | Detailed items need mapping to the correct project plan task IDs. | Close final mappings and confirm coverage completion. | 2026-03-06 | Daksh Hooda | Major | High | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25
15 | Issue | Quality | Quality | Some dashboard views still need refinement and visual consistency | Some parts of the solution still need polish to match expected presentation standards. | Retest impacted cases and refresh status counts after validation. | 2026-03-10 | Ujwala Makenna | Moderate | Average | Medium | 2026-03-25 | In-Progress | Mitigate | 2026-03-25
16 | Dependency | Stakeholder | Schedule | Business input is required for phase-wise requirement finalization | Delivery depends on timely business decisions and requirement confirmation. | Confirm owners and ETAs for the remaining mappings. | 2026-03-18 | Daksh Hooda | Major | High | High | 2026-03-25 | In-Progress | Mitigate | 2026-03-25
17 | Dependency | Technical | Schedule | Dashboard development depends on backend/API readiness | Some features cannot be validated without backend and API support. |  | 2026-03-18 | Lalith Gali | Major | Average | Medium | 2026-03-31 | Behind | Mitigate | 2026-03-25
18 | Dependency | Process | Schedule | UI refinement depends on working dashboard screens | UI enhancement can only happen after a usable version exists. |  | 2026-03-18 | Ujwala Makenna | Moderate | High | Medium | 2026-03-25 | Behind | Accept | 2026-03-25
19 | Dependency | Resource | Schedule | Testing and validation depend on completed phase builds | Testing cannot be completed until phase deliverables are ready. | Complete remaining access approvals and confirm dates. | 2026-03-18 | Daksh Hooda | Moderate | High | Medium | 2026-03-25 | In-Progress | Accept | 2026-03-25

## Stakeholder Register
Sr. No. | Name | Designation | Department | Role | Contact | Category | Interest | Influence | Category (Auto) | Expectations | Communication Type | Communication Frequency | Comms frequency | Comments
1 | Santhosh Nebalan | Program Manager | Project Management | Product Owner | santhosh.nebalan@zapcg.com | Internal | 3 | 5 | Keep Satisfied |  | Teams |  | Weekly
2 | Lalith Gali | Associate | Business Intelligence | Developer | lalith.gali@zapcg.com | Internal | 5 | 4 | Manage Closely |  | Teams |  | Daily
3 | Ujwala Makenna | Associate | Operations | UI/UX | ujwala.makenna@zapcg.com | Internal | 5 | 4 | Manage Closely |  | Teams |  | Daily
4 | Daksh Hooda | Associate | Project Management | Project Manager | daksh.hooda@zapcg.com | External | 5 | 4 | Manage Closely |  | Teams |  | Daily

## PM_Lists (hidden)
CadenceType | Frequency | GenericStatus | ResourceStatus | Criticality | Priority | ChangeStatus | Decision | UnavailabilityType | ImpactLevel | AvailabilityStatus | TaskType | ProjectPlanStatus | RAGStatus | MilestoneFlag | ProjectPhase
Governance | Daily | Planned | Requested | Critical | Critical | Submitted | Pending | Vacation | High | Planned | Task | Not Started | Red | ☐ | Initiation
Agile Ceremony | Weekly | Active | Confirmed | High | High | Under Review | Approved | Holiday | Medium | Approved | Milestone | In Progress | Amber | ☑ | Planning
Delivery Review | Bi-weekly | On Hold | Active | Medium | Medium | Approved | Rejected | Sick Leave | Low | Completed | Review | On Hold | Green |  | Execution
Working Session | Monthly | Closed | Rolled Off | Low | Low | Rejected | Deferred | Training |  | Cancelled | Decision | Completed |  |  | Testing
Leadership Review | Quarterly |  | Backfill Needed |  |  | Implemented |  | Partial Availability |  |  | Dependency | Delayed |  |  | UAT
| Once |  |  |  |  | Closed |  | Other |  |  |  | Cancelled |  |  | Deployment
| As Needed |  |  |  |  | Deferred | [8 empty] | Hypercare
Closure

## Governance & Cadences
Cadence ID | Forum / Meeting Name | Cadence Type | Audience / Participants | Frequency | Owner | Purpose / Objective | Key Output / Artifact | Duration | Status | Last Held On | Next Scheduled Date | Notes

## Resource Management Plan
Zapcom ID | Resource Name | Role | Workstream / Function | Allocation % | Start Date | End Date | Status | Criticality | Primary Manager / Lead | Backup / Secondary Owner | Notes | Allocation Status
| Santhosh Nebalan | Product Owner | [9 empty] | Unassigned
| Lalith Gali | Developer | [9 empty] | Unassigned
| Ujwala Makenna | UI/UX | [9 empty] | Unassigned
| Daksh Hooda | Project Manager | [9 empty] | Unassigned
| 0 | 0 | [9 empty] | Unassigned
| 0 | 0 | [9 empty] | Unassigned
| 0 | 0 | [9 empty] | Unassigned
| 0 | 0 | [9 empty] | Unassigned
ZC00340 | 0 | 0 | [9 empty] | Unassigned
| 0 | 0 | [9 empty] | Unassigned
0
0
0

## RACI Matrix
RACI MATRIX |  |  | Santhosh Nebalan | Daksh Hooda | Lalith Gali | Ujwala Makenna
PRIORITY | STATUS | PROJECT DELIVERABLE | Project Leadership |  |  |  | Team 1 | Team 2 | Other
PHASE 1 - Initiation
Low | In Progress | Request Review by PMO | C | R/A | I | I
Medium | Complete | Create Project Charter | C | R/A | I | I
High | Needs Review | Build Deliverable Scope | A | R | C | C
PHASE 2 - Planning and Design
High | Complete | Finalize requirements | C | R/A | C | I
High | Complete | Solution Design Sign-off | A | C | R | C
High | In Progress | Define Phase-wise Backlog | C | R/A | C | I
Medium | In Progress | Cconfirm dashboard | C | A | C | R
Medium | In Progress | Prioritize Phase Deliverables | C | R/A | C | I
PHASE 3 - Execution and Monitoring
High | Complete | Project View Development | I | C | R/A | C
High | In Progress | Portfolio View Development | I | C | R/A | C
High | Not Started | Performance View Development | I | C | R/A | C
High | Not Started | Staff Augmentation View Development | I | C | R/A | C
High | In Progress | Dashboard Metrics Implementation | I | C | R/A | C
Medium | In Progress | Excel Data Integration | I | C | R/A | I
Medium | In Progress | Backend API Support | I | C | R/A | I
Medium | In Progress | UI Review and Refinement | I | C | C | R/A
High | In Progress | Testing | I | R/A | C | C
High | In Progress | Progress Tracking | I | R/A | C | C
Medium | In Progress | RAID Tracking | I | R/A | C | C
Medium | In Progress | Stakeholder Reviews | A | R | I | I
PHASE 4 - Closing

## Resource Availability
Availability ID | Resource ID | Resource Name | Unavailability Type | Start Date | End Date | Days Impacted | Backup Assigned | Impact Level | Status | Notes
RAV-001
RAV-002
RAV-003
RAV-004
RAV-005
RAV-006
RAV-007
RAV-008
RAV-009
RAV-010

## Change Management Plan
Change ID | Date Submitted | Requester | Change Description | Reason / Driver | Impacted Area / Deliverable | Impact Summary | Priority | Owner | Status | Decision | Decision Date | Target Implementation Date | Follow-up / Notes
]