## Project Cover Sheet
Project Name
Integrated Project Management Workbook |  |  |  |  | RAG STATUS |  | AMBER
Project Overview |  |  | Schedule & Commercials
Project Name | Smartsync application |  | Start Date | 2025-07-01
Client | Smartsync |  | Forecast End | 2026-04-30
Project Manager | Suseela Nookala |  | Duration (Days) | 303
Project Sponsor | Ibrahim Houari |  | Budget | 60000
Complexity | High |  | Benefits | To build end to end integrations with PMS systems
Execution Snapshot |  | RAID Snapshot |  | Team & Governance
23 | 22 | 1 | 1 | 1 |  | 14
Total Tasks | Completed | Open Risks | Open Issues | Stakeholders |  | Resources
1 | 23 | 17 | 0 | 3
In Progress | Tracked Milestones | Open Dependencies | Change Requests | Cadences |  | Report Date
Quick Navigation & Notes
Use this sheet as the front page of the workbook. It pulls summary fields from Project Charter and high-level counts from the core tracking tabs. |  |  |  | Go to Project Charter |  | Go to Project Plan
Best practice: update Project Charter first, then maintain Project Plan / RAID / Stakeholder / Resource sheets. The cover sheet will reflect the latest picture.
|  |  |  | Go to RAID Dashboard |  | Go to Risk Register
Single source of truth for charter, schedule, RAID, stakeholders, resources, changes, and milestone tracking.
|  |  |  | Go to Stakeholders |  | Go to Milestones

## Project Charter
Smartsync application
Project Name: | Smartsync application |  | Project Manager: | Suseela Nookala |  |  | Project Sponsor: | Ibrahim Houari
Project Start Date: | 2025-07-01 |  | Estimated Duration: | 303 |  |  | Forecast End Date: | 2026-04-30
Estimated Budget: | 60000 |  | Estimated Benefits: | To build end to end integrations with PMS systems |  |  | Project Complexity: | High
Business Case: |  |  |  |  | Project Deliverables:
EOB Document Handling |  |  |  |  | BRD ,Detailed user stories
Scope: |  |  |  |  | Milestones:
Included |  | Excluded |  |  | ID | Milestone Title |  |  | Estimated Start | Estimated Finish
Secure web-based application architecture hosted on AWS Upload and process multi-page EOB documents Manual EOB separation and export to Open Dental Integration to Open Dental software only (Cloud and On-prem Versions) Admin panel for user management and access roles KPI dashboard for clinic performance and usage analytics Email-based two-factor authentication (2FA) Temporary cloud-based storage with automatic deletion policies Real Time Notifications with success, warning and errors as part EOB file upload All insurance sources are provided at the beginning of the project. Code repository hosted securely (e.g., GitHub or Firebase) Training documentation and demo environment |  | It is not currently possible to add supplemental payments (e.g., secondary or non-procedural payments) via the Open Dental API. |  |  |  | Project Kick Off |  |  | 2025-06-01 | 2025-06-01
Pre-signed S3 URLs for direct file uploads (minimizing PHI exposure) End-to-end encryption (HTTPS in transit, AES-256 at rest) Strict IAM policies and role-based access control Auto-expiry lifecycle policies on AWS S3 to enforce data retention limits CloudTrail setup for access logging and audit tracking Non-production environments will be seeded with anonymized or synthetic data only |  | The API only supports procedural payments at this time. |  |  |  | Requirements gathering |  |  | 2025-06-02 | 2025-06-10
|  | Supplemental payment functionality is on the Open Dental development roadmap, and it is expected (but not guaranteed) that it will be available in a future release. |  |  |  | Development |  |  | 2025-06-11 | 2025-09-02
[6 empty] | Testing (UAT,Regression) |  |  | 2025-09-03 | 2025-09-12
[6 empty] | Production |  |  | 2025-09-15 | 2025-09-15
[6 empty] | Production Maintenance |  |  | 2025-09-16 | 2025-04-30
Top 3 Risks:
ID | Risk/Issue Description | Risk Rating | Mitigation/Action Plan
HIGH
MEDIUM
LOW
Project Approval:

## Project Plan
Task ID | WBS | Phase | Task Name | Task Type | Predecessor ID | Owner | Support Team / Function | Planned Start Date | Planned End Date | Duration (Days) | Actual Start Date | Actual End Date | Status | % Complete | Add to Milestone Tracker | Baseline Start Date | Baseline End Date | Variance (Days) | RAG Status | Comments / Notes | _MilestoneSeq
T-001 | 1 | Initiation | Project Kickoff & Mobilization | PM / Governance |  | Suseela Nookala | PMO / Leadership | 2025-01-06 | 2025-01-06 | 1 | 2025-01-06 | 2025-01-06 | Completed | 100% | TRUE | 2025-01-06 | 2025-01-06 | 0 | Green |  | 1
T-002 | 1.1 | Initiation | SOW Commencement | Contract / Commercial | T-001 | Deepak Puranam/Sai Konda | PMO / Contracting | 2025-01-06 | 2025-06-06 | 152 | 2025-06-06 | 2025-06-06 | Completed | 100% | TRUE | 2025-06-06 | 2025-06-06 | 0 | Green |  | 2
T-003 | 1.2 | Planning | Planning | Planning / Scheduling | T-002 | Suseela Nookala | PMO / Delivery | 2025-12-06 | 2025-05-09 | -210 | 2025-12-06 | 2025-05-09 | Completed | 100% | TRUE | 2025-12-06 | 2025-05-09 | 0 | Green |  | 3
T-004 | 1.3 | Monitoring & Control | Weekly Governance & Stakeholder Reporting | PM / Governance | T-002 | Suseela Nookala | PMO / Client Governance | 2025-12-01 | 2026-06-10 | 192 | 2025-06-30 | 2025-06-30 | Completed | 100% | TRUE | 2025-06-30 | 2025-06-30 | 0 | Green |  | 4
T-005 | 1.4 | Planning | Change Request Scope Realignment & Re-baselining | Change Control / Scope | T-003 | Suseela Nookala | PMO / Leadership | 2025-03-06 | 2026-04-17 | 408 | 2025-06-30 | 2025-06-30 | Completed | 100% | TRUE | 2025-06-30 | 2025-06-30 | 0 | Green |  | 5
T-006 | 1.5 | Planning | Change Request Approval / Signature | Change Control / Scope | T-005 | Ibrahim/Sai | Leadership / Legal | 2025-04-06 | 2025-06-30 | 86 | 2025-04-06 | 2025-06-30 | Completed | 100% | TRUE | 2025-04-06 | 2025-06-30 | 0 | Green |  | 6
T-007 | 2 | Execution | User Authentication | Development | T-010 | Himansu Sekhar Bandha | Zapcom Team | 2025-06-11 | 2025-06-30 | 20 | 2025-06-11 | 2025-06-30 | Completed | 100% | TRUE | 2025-06-11 | 2025-06-30 | 0 | Green |  | 7
T-008 | 2.1 | Execution | Dashboard (Landing Screen) | Development | T-010 | Himansu Sekhar Bandha | Zapcom Team | 2025-06-11 | 2025-06-30 | 20 | 2025-06-11 | 2025-06-30 | Completed | 100% | TRUE | 2025-06-11 | 2025-06-30 | 0 | Green |  | 8
T-009 | 2.1 | Execution | EOB Upload | Development | T-010 | Himansu Sekhar Bandha | Zapcom Team | 2025-06-11 | 2025-07-08 | 28 | 2025-06-11 | 2025-07-08 | Completed | 100% | TRUE | 2025-06-11 | 2025-07-08 | 0 | Green |  | 9
T-010 | 2.3 | Execution | EOB Processing | Development | T-010 | Himansu Sekhar Bandha | Zapcom Team | 2025-06-11 | 2025-08-19 | 70 | 2025-06-11 | 2025-08-19 | Completed | 100% | TRUE | 2025-06-11 | 2025-08-19 | 0 | Green |  | 10
T-011 | 2.4 | Execution | Implement HIPAA-compliant processes | Development | T-010 | Himansu Sekhar Bandha | Zapcom Team | 2025-06-25 | 2025-07-22 | 28 | 2026-01-05 | 2026-03-31 | Completed | 100% | TRUE | 2026-01-05 | 2026-03-31 | 0 | Green |  | 11
T-012 | 2.5 | Execution | OpenDental API Integration | Development | T-010 | Himansu Sekhar Bandha | Zapcom Team | 2025-06-11 | 2025-07-22 | 42 | 2026-01-12 | 2026-03-31 | Completed | 100% | TRUE | 2026-01-12 | 2026-03-31 | 0 | Green |  | 12
T-013 | 2.6 | Execution | Performance Optimization | Development | T-011,T-012,T-013,T-014,T-015,T-016 | Himansu Sekhar Bandha | Zapcom Team | 2025-07-09 | 2025-08-19 | 42 | 2026-01-05 | 2026-03-31 | Completed | 100% | TRUE | 2026-01-05 | 2026-03-31 | 0 | Green |  | 13
T-014 | 2.7 | Execution | User Profile | Development | T-017 | Himansu Sekhar Bandha | Zapcom Team | 2025-07-23 | 2025-08-19 | 28 | 2026-02-02 | 2026-03-31 | Completed | 100% | TRUE | 2026-02-02 | 2026-03-31 | 0 | Green |  | 14
T-015 | 2.8 | Execution | Multi Clinic Capability | Development | T-018 | Himansu Sekhar Bandha | Zapcom Team | 2025-06-25 | 2025-08-19 | 56 | 2026-02-09 | 2026-03-31 | Completed | 100% | TRUE | 2026-02-09 | 2026-03-31 | 0 | Green |  | 15
T-016 | 2.9 | Execution | Reporting Dashboard | Development | T-019 | Himansu Sekhar Bandha | Zapcom Team | 2025-06-25 | 2025-07-22 | 28 | 2026-02-09 | 2026-03-31 | Completed | 100% | TRUE | 2026-02-09 | 2026-03-31 | 0 | Green |  | 16
T-017 | 2.1 | Execution | Regression Testing | QA Execution | T-022 | Suresh K | Zapcom Team | 2025-08-06 | 2025-08-09 | 4 | 2026-01-12 | 2026-03-31 | Completed | 100% | TRUE | 2026-01-12 | 2026-03-31 | 0 | Green |  | 17
T-018 | 2.11 | Execution | Automation Testing | QA Execution | T-023 | Suresh K | Zapcom Team | 2025-08-09 | 2025-08-19 | 11 | 2026-01-12 | 2026-04-17 | Completed | 100% | TRUE | 2026-01-12 | 2026-04-17 | 0 | Green |  | 18
T-019 | 2.12 | Execution | User Acceptance Testing | Testing | T-024 | Suresh K/Ibrahim Houari | Zapcom Team/Client | 2025-08-13 | 2025-08-19 | 7 | 2026-04-17 | 2026-04-17 | Completed | 100% | TRUE | 2026-04-17 | 2026-04-17 | 0 | Green |  | 19
T-020 | 2.13 | Execution | Production readiness and Deployment to Production | Production Readiness | T-019 | Suresh K/Ibrahim Houari | Zapcom Team/Client | 2025-09-15 | 2025-09-15 | 1 | 2025-09-15 | 2025-09-15 | Completed | 100% | TRUE | 2025-09-15 | 2025-09-15 | 0 | Green |  | 20
T-021 | 2.14 | Monitoring & Control | Production Validation | Testing | T-019 | Suresh K/Ibrahim Houari | Zapcom Team/Client | 2025-09-15 | 2025-09-15 | 1 | 2025-09-15 | 2025-09-15 | Completed | 100% | TRUE | 2025-09-15 | 2025-09-15 | 0 | Green |  | 21
T-022 | 2.15 | Monitoring & Control | UAT Sessions and Bug fixes | Jira / Resolution Tracting | T-019 | Suresh K/Ibrahim Houari | Zapcom Team/Client | 2025-09-15 | 2025-11-30 | 77 | 2025-09-15 | 2026-04-30 | Completed | 100% | TRUE | 2025-09-15 | 2025-11-30 | 151 | Green |  | 22
T-023 | 3.1 | Closure | Closure documentation | Jira / Resolution Tracting | T-021,T-022 | Suseela Nookala | PMO / Zapcom | 2026-05-01 | 2026-05-01 | 1 | 2026-05-01 | 2026-05-01 | In Progress | 100% | TRUE | 2026-05-01 | 2026-05-01 | 0 | Red |  | 23
| 3.2 | Monitoring & Control | [12 empty] | FALSE
| 3.3 | Monitoring & Control | [12 empty] | FALSE
| 4 | Monitoring & Control | [12 empty] | FALSE
| 4.1 | Monitoring & Control | [12 empty] | FALSE
| 4.2 | Monitoring & Control | [12 empty] | FALSE
| 4.3 | Closure | [12 empty] | FALSE
| 5 | Initiation | [12 empty] | FALSE
| 5.1 | Initiation | [12 empty] | FALSE
| 5.2 | Initiation | [12 empty] | FALSE
| 5.3 | Execution | [12 empty] | FALSE
| 5.4 | Execution | [12 empty] | FALSE
| 5.5 | Execution | [12 empty] | FALSE
| 5.6 | Planning | [12 empty] | FALSE
| 5.7 | Execution | [12 empty] | FALSE
| 5.8 | Execution | [12 empty] | FALSE
| 5.9 | Execution | [12 empty] | FALSE
| 5.1 | Execution | [12 empty] | FALSE
| 5.11 | Closure | [12 empty] | FALSE
| 6 | Planning | [12 empty] | FALSE
| 6.1 | Execution | [12 empty] | FALSE
| 6.2 | Execution | [12 empty] | FALSE
| 6.3 | Execution | [12 empty] | FALSE
| 6.4 | Execution | [12 empty] | FALSE
| 6.5 | Execution | [12 empty] | FALSE
| 6.6 | Closure | [12 empty] | FALSE
| 7 | Planning | [12 empty] | FALSE
| 7.1 | Planning | [12 empty] | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Formulas:
RAG Status = IF([Task ID]="","",IF([Status]="Completed","Green",IF(AND([Planned End Date]<>"",TODAY()>[Planned End Date]),"Red",IF(AND([Planned End Date]<>"",TODAY()+3>=[Planned End Date]),"Amber","Green"))))

## Milestone Tracker
Milestone Ref | WBS | Phase | Milestone / Task Name | Owner | Planned Start Date | Planned End Date | Actual End Date | Status | % Complete | Baseline End Date | Variance (Days) | RAG Status | Notes | _MilestoneSeq
T-001 | 1 | Initiation | Project Kickoff & Mobilization | Suseela Nookala | 2025-01-06 | 2025-01-06 | 2025-01-06 | Completed | 100% | 2025-01-06 | 0 | Green | 0 | 1
T-002 | 1.1 | Initiation | SOW Commencement | Deepak Puranam/Sai Konda | 2025-01-06 | 2025-06-06 | 2025-06-06 | Completed | 100% | 2025-06-06 | 0 | Green | 0 | 2
T-003 | 1.2 | Planning | Planning | Suseela Nookala | 2025-12-06 | 2025-05-09 | 2025-05-09 | Completed | 100% | 2025-05-09 | 0 | Green | 0 | 3
T-004 | 1.3 | Monitoring & Control | Weekly Governance & Stakeholder Reporting | Suseela Nookala | 2025-12-01 | 2026-06-10 | 2025-06-30 | Completed | 100% | 2025-06-30 | 0 | Green | 0 | 4
T-005 | 1.4 | Planning | Change Request Scope Realignment & Re-baselining | Suseela Nookala | 2025-03-06 | 2026-04-17 | 2025-06-30 | Completed | 100% | 2025-06-30 | 0 | Green | 0 | 5
T-006 | 1.5 | Planning | Change Request Approval / Signature | Ibrahim/Sai | 2025-04-06 | 2025-06-30 | 2025-06-30 | Completed | 100% | 2025-06-30 | 0 | Green | 0 | 6
T-007 | 2 | Execution | User Authentication | Himansu Sekhar Bandha | 2025-06-11 | 2025-06-30 | 2025-06-30 | Completed | 100% | 2025-06-30 | 0 | Green | 0 | 7
T-008 | 2.1 | Execution | Dashboard (Landing Screen) | Himansu Sekhar Bandha | 2025-06-11 | 2025-06-30 | 2025-06-30 | Completed | 100% | 2025-06-30 | 0 | Green | 0 | 8
T-009 | 2.1 | Execution | EOB Upload | Himansu Sekhar Bandha | 2025-06-11 | 2025-07-08 | 2025-07-08 | Completed | 100% | 2025-07-08 | 0 | Green | 0 | 9
T-010 | 2.3 | Execution | EOB Processing | Himansu Sekhar Bandha | 2025-06-11 | 2025-08-19 | 2025-08-19 | Completed | 100% | 2025-08-19 | 0 | Green | 0 | 10
T-011 | 2.4 | Execution | Implement HIPAA-compliant processes | Himansu Sekhar Bandha | 2025-06-25 | 2025-07-22 | 2026-03-31 | Completed | 100% | 2026-03-31 | 0 | Green | 0 | 11
T-012 | 2.5 | Execution | OpenDental API Integration | Himansu Sekhar Bandha | 2025-06-11 | 2025-07-22 | 2026-03-31 | Completed | 100% | 2026-03-31 | 0 | Green | 0 | 12
T-013 | 2.6 | Execution | Performance Optimization | Himansu Sekhar Bandha | 2025-07-09 | 2025-08-19 | 2026-03-31 | Completed | 100% | 2026-03-31 | 0 | Green | 0 | 13
T-014 | 2.7 | Execution | User Profile | Himansu Sekhar Bandha | 2025-07-23 | 2025-08-19 | 2026-03-31 | Completed | 100% | 2026-03-31 | 0 | Green | 0 | 14
T-015 | 2.8 | Execution | Multi Clinic Capability | Himansu Sekhar Bandha | 2025-06-25 | 2025-08-19 | 2026-03-31 | Completed | 100% | 2026-03-31 | 0 | Green | 0 | 15
T-016 | 2.9 | Execution | Reporting Dashboard | Himansu Sekhar Bandha | 2025-06-25 | 2025-07-22 | 2026-03-31 | Completed | 100% | 2026-03-31 | 0 | Green | 0 | 16
T-017 | 2.1 | Execution | Regression Testing | Suresh K | 2025-08-06 | 2025-08-09 | 2026-03-31 | Completed | 100% | 2026-03-31 | 0 | Green | 0 | 17
T-018 | 2.11 | Execution | Automation Testing | Suresh K | 2025-08-09 | 2025-08-19 | 2026-04-17 | Completed | 100% | 2026-04-17 | 0 | Green | 0 | 18
T-019 | 2.12 | Execution | User Acceptance Testing | Suresh K/Ibrahim Houari | 2025-08-13 | 2025-08-19 | 2026-04-17 | Completed | 100% | 2026-04-17 | 0 | Green | 0 | 19
T-020 | 2.13 | Execution | Production readiness and Deployment to Production | Suresh K/Ibrahim Houari | 2025-09-15 | 2025-09-15 | 2025-09-15 | Completed | 100% | 2025-09-15 | 0 | Green | 0 | 20
T-021 | 2.14 | Monitoring & Control | Production Validation | Suresh K/Ibrahim Houari | 2025-09-15 | 2025-09-15 | 2025-09-15 | Completed | 100% | 2025-09-15 | 0 | Green | 0 | 21
T-022 | 2.15 | Monitoring & Control | UAT Sessions and Bug fixes | Suresh K/Ibrahim Houari | 2025-09-15 | 2025-11-30 | 2026-04-30 | Completed | 100% | 2025-11-30 | 151 | Green | 0 | 22
T-023 | 3.1 | Closure | Closure documentation | Suseela Nookala | 2026-05-01 | 2026-05-01 | 2026-05-01 | In Progress | 100% | 2026-05-01 | 0 | Red | 0 | 23

## RAID Log
RAID ID | Type | Category | Impact Area | Title | Description | Impact/Effect of the RAID | Date Raised | RAID Owner | Impact Rating | Initial Probability | Severity | Target Date | Status | Mitigation Strategy | Next Update | Closed Date | RAID Response/Plan | Risk Seq
1 | Risk | Scope | Schedule | To improve the AI model's accuracy to achieve results | To improve the AI model's accuracy to achieve results |  | 2026-06-20 | Manjunath Sirur, Andrew team | Severe | Severe | High | July 30 2025 | Closed | Mitigate |  | July 30 2025 | Team is working to optimise the AI models. Detailed report to be shared by manju - ETA - 14 -Aug-2025
2 | Issue | Technical | Schedule | Team to work on the analysis for connecting the Open dental | Team to work on the analysis for connecting the Open dental |  | 2025-07-17 | Andrew,Himansu | Severe | Severe | High | July 25 2025 | Closed | Accept |  | July 25 2025 | Himansu has shared the details and 7, 8 action items to be completed
3 | Issue | Process | Schedule | To provide access to the Dr.Ibrahim for him to start early testing | To provide access to the Dr.Ibrahim for him to start early testing |  | 2025-07-17 | Mani Chandana, Back End team | Major | Major | High | Aug 1 2025 | Closed | Avoid |  | Aug 1 2025 | Team is working on setting up in separate environment .
4 | Issue | Security/Compliance | Schedule | Team to work on the cost on the sftp instance and provide an update on to Dr.Ibrahim | Team to work on the cost on the sftp instance and provide an update on to Dr.Ibrahim |  | 2025-07-21 | Santhana and Andrew | Moderate | Moderate | High | July 25 2025 | Closed | Mitigate |  | July 25 2025 | Andrew has shared the costing options and doctor confirmed to go ahead.
5 | Issue | Process | Schedule | Team to share the cost details related to change requests of additional scope. | Team to share the cost details related to change requests of additional scope. |  | 2025-07-21 | Len Summa, Sai Siddarth | Moderate | Moderate | High | July 25 2025 | Closed | Accept |  | July 25 2025 | Len and Siddarth is going to discuss with Dr and provide next updates.
6 | Issue | Security/Compliance | Schedule | Team to discuss in detail with Dr.Ibrahim about the account page,AI Page,Manual processing button ,notification settings | Team to discuss in detail with Dr.Ibrahim about the account page,AI Page,Manual processing button ,notification settings |  | 2025-07-21 | Himansu | Moderate | Moderate | High | July 25 2025 | Closed | Avoid |  | July 25 2025 | Call is completed and requirments clarifications are completed
7 | Issue | Stakeholder | Schedule | Need to share with doctor List of API and set up images for the Developer portal access | Need to share with doctor List of API and set up images for the Developer portal access |  | 2025-07-24 | Andrew,Himansu | Moderate | Moderate | Medium | July 28 2025 | Closed | Mitigate |  | July 28 2025 | Andrew and Himansu will share the list
8 | Issue | Process | Schedule | Need to share the document by correcting the images without patient data and to be slide presentation | Need to share the document by correcting the images without patient data and to be slide presentation |  | 2025-07-24 | Himansu | Minor | Minor | Medium | July 28 2025 | Closed | Accept |  | July 28 2025 | Himansu to update the details and share it
9 | Issue | Technical | Schedule | Need to share the tax ID validation steps from any website (IRS) and the format of tax ID to be corrected | Need to share the tax ID validation steps from any website (IRS) and the format of tax ID to be corrected |  | 2025-07-24 | Himansu,Andrew | Moderate | Moderate | Medium | July 31 2025 | Closed | Avoid |  | July 31 2025 | it was concluded no third party will be used
10 | Issue | Process | Schedule | Set of examples to be shared by Doctor by tax ID and picture how the clinic should look alike | Set of examples to be shared by Doctor by tax ID and picture how the clinic should look alike |  | 2025-07-24 | Dr.Ibrahim | Major | Major | Low | July 25 2025 | Closed | Mitigate |  | July 25 2025 | Doctor has shared requested details
11 | Issue | Process | Schedule | Team to get back on the email 2 way authentication | Team to get back on the email 2 way authentication |  | 2025-07-24 | Andrew,Himansu | Minor | Minor | Medium | July 28 2025 | Closed | Accept |  | July 28 2025 | Himansu and Andrew to discuss on the technical challenges
12 | Issue | Technical | Schedule | Smartsync needs to be added in email forgot password functionality and create new password should show up in screen | Smartsync needs to be added in email forgot password functionality and create new password should show up in screen |  | 2025-07-28 | Himansu and Team | Moderate | Moderate | Medium | Aug 19 2025 | Closed | Avoid |  | Aug 19 2025 | Team will be taking up as an enhancements and fix the UI changes in the current sprint and complete
13 | Issue | Technical | Schedule | All UI related changes will be incorporated in upcoming sprints Replace “Open Dental” with more general “PMS integration” in notification terminology Remove the dash in the Tax ID field label (use “TaxID”) for consistent formatting Reorder address input fields to follow U.S. conventions: Address → City → State → ZIP Code In the Add Location form: Display only the logged‑in admin’s name, not a dropdown In user/account edit screens: Make admin name and email fields read‑only, and non‑clickable | All UI related changes will be incorporated in upcoming sprints Replace “Open Dental” with more general “PMS integration” in notification terminology Remove the dash in the Tax ID field label (use “TaxID”) for consistent formatting Reorder address input fields to follow U.S. conventions: Address → City → State → ZIP Code In the Add Location form: Display only the logged‑in admin’s name, not a dropdown In user/account edit screens: Make admin name and email fields read‑only, and non‑clickable |  | 2025-07-28 | Himansu and Team | Moderate | Moderate | Medium | Aug 19 2025 | Closed | Mitigate |  | Aug 19 2025 | Team will be taking up as an enhancements and fix the UI changes in the current sprint complete
14 | Issue | Technical | Schedule | Design and streamline the workflow that links Ibrahim’s login to his assigned location within Smart Sync Dental, and clearly demonstrate how the connection is established. | Design and streamline the workflow that links Ibrahim’s login to his assigned location within Smart Sync Dental, and clearly demonstrate how the connection is established. |  | 2025-08-06 | Andrew,Himansu | Moderate | Moderate | High | Aug 13 2025 | Closed | Accept |  | Aug 13 2025
15 | Issue | Quality | Schedule | Feedback from doctor in staging environment | Feedback from doctor in staging environment |  | 2025-08-11 | Zapcom Team | Moderate | Moderate | High | Aug 19 2025 | Closed | Avoid |  | Aug 19 2025 | Team to share the plan with doctor for the fixes
16 | Issue | Stakeholder | Schedule | Domain regards and BAA agreement | Domain regards and BAA agreement |  | 2025-08-11 | Dr.Ibrahim and zapcom Infra team | Moderate | Moderate | High | Aug 30 2025 | Closed | Accept |  | Aug 30 2025 | Team to share the required details with doctor and next steps detailed discussion will be planned
17 | Issue | Process | Schedule | A SES account needed for converting to production | A SES account needed for converting to production |  | 2025-08-12 | Andrew ,Md shamim,Mani Chandana | Moderate | Moderate | High | Aug 19 2025 | Closed | Avoid |  | Aug 19 2025 | A business needs to be submitted by dev team.
18 | Dependency | Quality | Schedule
19 | Dependency | Security/Compliance | Schedule
20 | Dependency | Technical | Schedule
21 | Dependency | Stakeholder | Schedule
22 | Dependency | Stakeholder | Other
23 | Dependency | Technical | Schedule
24 | Dependency | Technical | Schedule
25 | Dependency | Security/Compliance | Security/Compliance
26 | Dependency | Security/Compliance | Schedule
27 | Dependency | Technical | Schedule
28 | Dependency | Technical | Schedule
29 | Dependency | Process | Schedule
30 | Dependency | Technical | Schedule
31 | Dependency | Technical | Schedule
32 | Dependency | Technical | Schedule
33 | Risk | Stakeholder | Schedule
34 | Issue | Technical | Schedule
35 | Dependency | Stakeholder | Schedule
36 | Dependency | Stakeholder | Schedule

## Risk Register
ID | Helper_Row | Risk Description | Risk Effect on Objectives | Impact Area | Impact Category | Impact Rating | Probability | Risk Score | Risk Priority | Risk Ranking | Status | Risk Owner | Date Raised | Closed Date | Mitigation Strategy | Risk Response

## Stakeholder Register
Sr. No. | Name | Designation | Department | Role | Contact | Category | Interest | Influence | Category (Auto) | Expectations | Communication Type | Communication Frequency | Comms frequency | Comments
1 | Ibrahim Hoauri | Doctor | Project Sponser | Client | smartsyncdental@gmail.com | External | 5 | 5 | Manage Closely |  | Email |  | Daily
2
3
4
5
6
7
8
9
10
11
12

## PM_Lists (hidden)
CadenceType | Frequency | GenericStatus | ResourceStatus | Criticality | Priority | ChangeStatus | Decision | UnavailabilityType | ImpactLevel | AvailabilityStatus | TaskType | ProjectPlanStatus | RAGStatus | MilestoneFlag | ProjectPhase
Governance | Daily | Planned | Requested | Critical | Critical | Submitted | Pending | Vacation | High | Planned | Task | Not Started | Red | ☐ | Initiation
Agile Ceremony | Weekly | Active | Confirmed | High | High | Under Review | Approved | Holiday | Medium | Approved | Milestone | In Progress | Amber | ☑ | Planning
Delivery Review | Bi-weekly | On Hold | Active | Medium | Medium | Approved | Rejected | Sick Leave | Low | Completed | Review | On Hold | Green |  | Execution
Working Session | Monthly | Closed | Rolled Off | Low | Low | Rejected | Deferred | Training |  | Cancelled | Decision | Completed |  |  | Testing
Leadership Review | Quarterly |  | Backfill Needed |  |  | Implemented |  | Partial Availability |  |  | Dependency | Delayed |  |  | UAT
| Once |  |  |  |  | Closed |  | Other |  |  |  | Cancelled |  |  | Deployment
| As Needed |  |  |  |  | Deferred | [8 empty] | Hypercare
Closure

## Governance & Cadences
Cadence ID | Forum / Meeting Name | Cadence Type | Audience / Participants | Frequency | Owner | Purpose / Objective | Key Output / Artifact | Duration | Status | Last Held On | Next Scheduled Date | Notes
CAD-001 | Daily Standup | Agile Ceremony | Team Members | Daily | Scrum Master / Product Owner | N/A | N/A | 15 mins | Active | N/A | N/A
CAD-002 | Weekly status review | Delivery Review | Stakeholders - SLTs | Weekly | Program Manager | N/A | N/A | N/A | Active | N/A | N/A
CAD-003 | Weekly Connect with Doctor and Zapcom team | Working Session | Zapcom QA and Accelya QA | Weekly | Zapcom QA | N/A | N/A | 45 mins | Active | N/A | N/A

## RACI Matrix
RACI MATRIX
PRIORITY | STATUS | PROJECT DELIVERABLE | Project Leadership |  |  |  |  | Team 1 |  |  |  | Team 2 |  |  |  | Agency POC |  |  |  |  | Others
PHASE 1 - Initiation
Low | In Progress
Medium | Complete
PHASE 2 - Planning and Design
|  | Access, environment, and tool setup | I | I | I | R | C | C | R | C | C | C | R | C | C | C | C | C |  |  | R
|  | Current-state process / system / API review | I | I | C | A | C | R | R | C | C | R | R | C | C | C | R | C | C | C |  | C
|  | Future-state standard / target-state review | I | C | C | C | I | R | C | I | I | R | C | I | I | C | R | C | C | C |  | A/R
|  | Gap analysis approach and test strategy definition | I | C | C | A | C | R | R | I | I | R | R | I | I | C | C | C | I | I |  | C
|  | Test scenario and test case identification | I | I | C | A | C | R | R | C | C | R | R | C | C | C | C | I | I | I |  | C
|  | Test data preparation | I | I | C | A | C | C | R | R | R | C | R | R | R | C | C | R | R | R |  | C
PHASE 3 - Execution and Monitoring
|  | Test execution and validation | I | I | I | A | I | C | R | R | R | C | R | R | R | C | C | R | R | R |  | C
|  | Defect / issue triage and clarification management | I | I | I | A | I | R | R | C | C | R | R | C | C | C | R | C | I | I |  | R
|  | Gap classification and impact assessment | I | I | I | A | I | R | C | I | I | R | C | I | I | C | R | C | I | I |  | C
|  | JIRA / backlog / user story documentation | I | I | I | A | I | R | C | I | I | R | C | I | I | C | R | C | I | I |  | C
|  | Dependency and risk management | C | I | I | A/R | R | C | C | I | I | C | C | I | I | C | C | I | I | I |  | C
|  | Weekly status reporting and stakeholder communication | I | I | I | R | I | C | C | I | I | C | C | I | I | C | C | I | I | I |  | I
|  | Change control / scope management | I | C | C | A/R | C | C | I | I | I | C | I | I | I | C | C | I | I | I |  | C
PHASE 4 - Closing
|  | Final gap analysis report and handoff | I | C | C | A | C | R | C | I | I | R | C | I | I | C | R | C | I | I |  | C
|  | Project Closing Approval | I | C | C | R | C | I | I | I | I | I | I | I | I | I | I | I | I | I |  | A

## Change Management Plan
Change ID | Date Submitted | Requester | Change Description | Reason / Driver | Impacted Area / Deliverable | Impact Summary | Priority | Owner | Status | Decision | Decision Date | Target Implementation Date | Follow-up / Notes

## Resource Management Plan
Zapcom ID | Resource Name | Role | Workstream / Function | Allocation % | Start Date | End Date | Status | Criticality | Primary Manager / Lead | Backup / Secondary Owner | Notes | Allocation Status
NA | Santhanakrishnan | Engineering Manager | Engineering Manager | 25% | 2025-05-15 | 2025-10-31 | Active | Critical | Prasanth |  |  | Planned
ZCU0025 | Andrew | Tech Lead | Developer | 100% | 2025-05-01 | 2025-09-22 | Rolled Off | Critical | Eswaran Pragasam |  |  | High Allocation
ZC00590 | Md Shamim | Sr Backend Dev | Developer | 100% | 2025-06-15 | 2026-04-30 | Active | Critical | Srikanthan Adarsh |  |  | High Allocation
ZCU0019 | Nagavarshini Surapaneni | Jr Backend Dev | Developer | 100% | 2025-06-15 | 2025-12-15 | Active | Critical | Patil |  |  | High Allocation
ZC00320 | Mani chandana | Sr DevOps | DevOps | 100% | 2025-06-15 | 2026-04-30 | Active | High | Patil |  |  | High Allocation
ZC00623 | Steeven Raj | FrontEnd Dev | Developer | 100% | 2025-06-15 | 2026-04-30 | Active | Medium | Patil |  |  | High Allocation
ZC00673 | Rashmi Ranjan | Sr FrontEnd Dev | Developer | 100% | 2025-06-15 | 2026-04-30 | Active | Medium | Patil |  |  | High Allocation
ZC00766 | Himansu Sekhar | BA | Business Analyst | 100% | 2025-06-15 | 2026-04-30 | Active | Medium | Swathi Dharshana |  |  | High Allocation
ZC00709 | Suresh kuruva | Testing | Testing | 100% | 2025-06-15 | 2026-04-30 | Active | Medium | Uma Vigneshwar Bhat |  |  | High Allocation
ZC00536 | Suseela Nookala | Scrum master | Project management | 50% | 2025-07-22 | 2026-04-30 | Active | Critical | Jane Angelin |  |  | Planned
ZC00753 | Guhana Velayutham | Customer Success Partner | Customer Success | 25% | 2025-09-22 | 2026-07-31 | Active | High | Deepak puranam |  |  | Planned
ZC00694 | Lavanya Uppala | Testing | Testing | 50% | 2025-08-20 | 2025-12-15 | Rolled Off | High | Uma Vigneshwar Bhat |  |  | Planned
ZC00214 | Manjunath Sirur | Data lead | Developer | 50% | 2025-07-07 | 31-09-2026 | Rolled Off | High | Patil |  |  | Planned
ZCU0045 | Ramakrishna reddy molakaseena | Data engineer | Developer | 100% | 2025-06-15 | 2026-04-30 | Active | High | Eswaran Pragasam |  |  | High Allocation

## Resource Availability
Availability ID (Auto Updates) | Resource ID | Resource Name | Unavailability Type | Start Date | End Date | Days Impacted | Backup Assigned | Impact Level | Status | Notes